## Gantt Chart
BrightTV Viewership Analytics — Project Gantt Chart ¦ 1 Apr 2026 – 15 Apr 2026
Data & Setup |  |  |  | Analysis |  |  |  | Insights & Recommendations |  |  |  | Presentation |  |  |  | Delivery |  | Milestone (◆)
Phase | Task / Milestone | Duration | 1 Wed | 2 Thu | 3 Fri | 4 Sat | 5 Sun | 6 Mon | 7 Tue | 8 Wed | 9 Thu | 10 Fri | 11 Sat | 12 Sun | 13 Mon | 14 Tue | 15 Wed
Data & Setup
| Data ingestion & schema review | 2 days
| Data cleaning & null checks | 3 days
| UTC → SA timezone conversion | 2 days
Analysis
| Session metrics analysis | 3 days
| User-level aggregations | 4 days
| Demographic breakdown | 3 days
| Channel popularity analysis | 3 days
| ◆ Analysis sign-off | Milestone | [8 empty] | ◆
Insights & Recommendations
| Consumption factor analysis | 3 days
| Low-consumption day content recs | 3 days
| User base growth initiatives | 3 days
Presentation
| Slide deck creation | 3 days
| Internal review & refinements | 2 days
| ◆ Presentation ready | Milestone | [13 empty] | ◆
Delivery
| CEO / CVM presentation delivery | 1 day
| ◆ Project complete | Milestone | [14 empty] | ◆